## Start schema
Table name | Table DDL in Git (Y/N) | Source View DDL in Git (Y/N) | In CNF_DW_REFRESH (Y/N) | Populated (Y/N) | Developer | Comments
DIM_DATE_TIME | Y | Y |  | Y
DIM_DISCHAGE_TYPES | Y | Y | Y | Y | Steve | Steve will re-populate this table with new sequence, trigger, trim/intcap name.
DIM_HC_DEPARTMENTS | Y | Y | Y | Y | Oleg
DIM_HC_FACILITIES | Y | N | N | Y | Oleg
DIM_HC_NETWORKS | Y | N | N | Y | Oleg | No need for a view or CNF entry. DML included into DDL script.
DIM_PAYERS | Y | N | Y | Y | Oleg | Data is currently coming from PT008.PAYER_MAPPING. We need to implement the same logic in a source view and remove this dependency from PT008.
DIM_PROCEDURES | Y | Y | Y | Y | Oleg
DIM_PROVIDERS | Y | N | N | Y | Ganesh
DIM_RX | N | N | N | Y | Uma | Oleg: this is not a DIM* table! It has 175 M rows.
DIM_VISIT_SERVICE_TYPES | N | N | N | Y | Steve | Instead ot this table, create synonym REF_VISIT_SERVICE_TYPES -> VISIT_SERVICE_TYPE. Add table FACT_VISIT_SERVICES - see below.
REF_DIAGNOSES | Y | Y | Y | Y | Oleg
REF_DRUG_DESCRIPTIONS | N | N | N | Y | Steve
REF_HC_SPECIALTIES | Y | Y | Y | Y | Oleg
REF_ORDER_TYPES | Y | N/A | Y | Y | Oleg | View is not needed
REF_PROC_EVENT_ARCHIVE_TYPES | Y | N/A | Y | Y | Oleg | View is not needed
REF_PROC_EVENT_PROVIDER | N | N | N | Y | Steve | Steve is going to move this data to FACT_VISIT_METRIC_RESULTS . Then he will drop this table.
REF_VISIT_TYPES | Y | N/A | Y | Y | Oleg | View is not needed
MAP_DIAGNOSES_CODES | Y | Y | Y | Y | Oleg
MAP_DISCHARGE_TYPE | N | N | N | Y | Steve | See DIM_DISCHARGE_TYPES above
MAP_VISIT_SERVICE_TYPE | N | N | N | Y | Steve | Not needed. See DIM_VISIT_SERVICE_TYPES above
FACT_PATIENT_DIAGNOSES | N | N | N | Y | Steve
FACT_PATIENT_PRESCRIPTIONS | Y | Y | Y | Y | Steve | Need to replicate functionality from PT005.
FACT_RESULTS | Y | Y | Y | N | Ganesh
FACT_VISITS | Y | Y | Y | N | Ganesh
FACT_VISIT_METRIC_RESULTS | Y | N | N | Y | Steve
FACT_VISIT_PAYERS | N | N | N | N | Steve | Steve will do everything except CNF entry. Oleg will do CNF.
FACT_VISIT_SERVICES | N | N | N | N | Steve | To be created. Based mainly on VISIT_SEGMENT.
STG_MUNICIPALITIES | N | N | N | Y | Oleg | I purchased US ZIP code database and loaded it into this table, paid $40.
REF_ZIP_CODES | N | N | N | Y
REF_MUNICIPALITIES | N | N | N | Y